## Sheet1
MSc. Project
BecA-ILRI Hub
Margaret Wanjiku
TASK NAME | ASSIGNED TO | START DATE | DUE DATE | DURATION | % DONE | DESCRIPTION | PRIORITY | SPRINT/MILESTONE
Task 1 | Margaret Wanjiku | 2019-09-02 | 2019-09-30 | 28 |  | Developing project concept |  | Phase 1
Task 2 | Margaret Wanjiku | 2019-10-01 | 2019-10-31 | 30 |  | Proposal writing |  | Phase 1
Task 3 | Margaret Wanjiku | 2019-11-04 | 2019-11-08 | 4 |  | Proposal presentation at Pwani University |  | Phase 1
Task 4 | Margaret Wanjiku | 2019-11-11 | 2020-03-31 | 141 |  | Data analysis |  | Phase 1
Task 5 | Margaret Wanjiku | 2020-04-01 | 2020-06-10 | 70 |  | MSc. Dissertation writing |  | Phase 1
Task 6 | Margaret Wanjiku | 2020-06-22 | 2020-06-26 | 4 |  | MSc. Dissertation presentation at Pwani University |  | Phase 2
Task 7 | Margaret Wanjiku | 2020-07-01 | 2020-09-30 | 91 |  | Corrections/ revisions of MSc. Dissetation and writing of manuscripts to be submitted to a journal |  | Phase 2